## Sheet1
Task | Assigned To | Estimated Time | Actual Time | Status
Implement PDF source and notes in Desktop APP | Jeffrey E | 3 hours | 15 hours | Complete
Add Support for Video in WebApp | Gavin C | 10 hours | 12 hours | Complete
Update Upload Source Page to handle multiple SourceTypes | Jeffrey E | 1.5 hours | 4 hours | Complete
Format Source/ Note Viewer page to be side by side | Gavin C | 1 hour | 2 hours | Complete
Add input validation for account creation and metadata | Jeffrey E | 1 hour | 3 hours | Complete