## Sheet1
Task | Assigned To | Estimated Time | Actual Time | Status
Video capabilities for DesktopApp | Jeffrey E | 5 hours | 3 hours | Complete
Video capabilities for WebApp | Gavin C | 2 | 2 | Complete
Add Remove Note functionality on DesktopApp | Jeffrey E | 2 hours | 2-3 hours | Complete
Add Remove Note functionality on WebApp | Gavin C | 2 hours | 2 hours | Complete
Add Remove Source with Notes on DesktopApp | Jeffrey E | 2 hours | 1 hour | Complete
Add Remove Source with Notes on WebApp | Gavin C | 2 hours | 2 hours | Complete
Allow Edit Notes functionality on DesktopApp | Jeffrey E | 3 hours | 4-5 hours | Complete
Allow Edit Notes functionality on WebApp | Gavin C | 2 hours | 2 hours | Complete