## Sheet1
Action | Task | Assigned To | Estimated Time | Actual Time | Status
Add backend capabilities for tags (Controller, model) | Manage Tags | Gavin | 4 hours | 3 hours | Complete
Add module to display note tags per note | Manage Tags | Gavin | 3 hours | 5 hours | Complete
Add functionality to add/remove a tag | Manage Tags | Gavin | 3 hours | 3 hours | Complete
Add backend capabilities for finding Notes by tag | Find Notes | Gavin | 4 hours | 5 hours | Complete
Add front end page to allow for Note-Finding | Find Notes | Gavin | 5 hours | 4 hours | Complete
Allow for tag filtering and sorting note results | Find Notes | Gavin | 3 hours |  | Incomplete
Fix web page reponsive issues | Address Noted Concerns | Gavin | 2 hours |  | Incomplete
Add cancel to editing notes | Address Noted Concerns | Gavin | 2 hours |  | Incomplete
Adding Model and DAL Connections to Tags and NoteTags in Desktop App | Manage Tags | Jeffrey | 3 hours | 4 hours | Complete
Add Inserting and Viewing Tags in the Desktop Application | Manage Tags | Jeffrey | 2 hours | 5 hours | Complete
Added removing Tag functionalities in Desktop Application and Database | Manage Tags | Jeffrey | 1 hour | 0.5 hours | Complete
Added Note Searching by Multiple Partial-Tag filtering in Desktop App | Find Notes | Jeffrey | 4 hours | 7 hours | Complete
Allow Note Ordering based on matching applied tags while searching in Desktop App | Find Notes | Jeffrey | 1 hour |  | Incomplete
Added code Documentation in Desktop App | Address Noted Concerns | Jeffrey | 1 hour | 1 hour | Complete