## Sheet1
Action | Task | Assigned To | Estimated Time | Actual Time | Status
Add backend capabilities for tags (Controller, model) | Manage Tags | Gavin | 4 hours | 3 hours | Complete
Add module to display note tags per note | Manage Tags | Gavin | 3 hours | 5 hours | Complete
Add fucntionality to add/remove a tag | Manage Tags | Gavin | 3 hours
Add backend capabilities for finding Notes by tag | Find Notes | Gavin | 4 hours
Add front end page to allow for Note-Finding | Find Notes | Gavin | 5 hours
Allow for tag filtering and sorting note results | Find Notes | Gavin | 3 hours